## Budget
Task | Task Name & Short Description | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | PER TASK TOTAL
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1 | [17 empty] | 0
|  | $ |  |  |  | $ |  |  |  | $ |  |  |  | $
2 | [17 empty] | 0
0
3 | [17 empty] | 0
$
4 | [17 empty] | 0
$
5 | [17 empty] | 0
$
6 | [17 empty] | 0
$
7 | [17 empty] | 0
$
8 | [17 empty] | 0
|  | $ |  |  |  | $ |  |  |  | $ |  |  |  | $
9 | Indirect costs are allowed up to the Tribe’s federaly negotiated indirect cost rate. If the Tribe does not have a negotiated rate, indirect costs may be charged up to a maximum of 15% | [16 empty] | 0
|  | $ |  |  |  | $ |  |  |  | $ |  |  |  | $
10 | Administrative: Reporting, Project Management, Invoicing (auto-calculated at 10% of total of project cost, payable to tribe) | [16 empty] | 0 | bar: 2026 Q4 to 2029 Q4
|  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
GRAND TOTAL FOR PROJECT (not to exceed $3 million) | [17 empty] | 0

## Example Budget
Task | Task Name & Short Description | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029 |  |  |  | PER TASK TOTAL
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
1 | Environmental Review & Site Assessments: Includes hydrologic studies, soil sampling, environmental impact reviews, and cultural resource analysis necessary to determine feasibility and placement of sewage system infrastructure serving new affordable housing units. | [16 empty] | 35000 | bar: 2026 Q1 to 2027 Q2
|  | 15000 |  |  |  | 20000
2 | Conceptual Engineering & Feasibility Design: Covers system sizing, capacity modeling, conceptual sewer line layout, and feasibility studies to confirm infrastructure requirements for the planned affordable housing development. | [16 empty] | 30000 | bar: 2026 Q1 to 2026 Q3; 2027 Q2 to 2028 Q1
|  | 0 |  |  |  | 25000 |  |  |  | 5000
3 | Community Engagement & Tribal Consultation: Supports outreach to Tribal citizens and community/regional partners regarding placement, cultural considerations, and construction impacts of the new sewage system required for affordable housing. | [16 empty] | 60000
|  | 5000 |  |  |  | 20000 |  |  |  | 20000 |  |  |  | 20000
4 | Financial Modeling, Rate Study & Funding Strategy: Includes long-term cost modeling, sewer rate implications, and funding pathway development to ensure affordability and sustainability of the sewage system supporting new housing. | [16 empty] | 30000 | bar: 2026 Q1 to 2027 Q2
|  | 10000 |  |  |  | 20000
5 | Architectural / Engineering Technical Services: Provides engineering support for design alternatives, system alignment, lift station planning, and infrastructure integration for the new affordable housing area. | [16 empty] | 165000 | bar: 2026 Q1 to 2027 Q4
|  | 15000 |  |  |  | 150000
6 | Construction and Implementation | [16 empty] | 1950000 | bar: 2026 Q1 to 2026 Q3; 2028 Q1 to 2029 Q2
|  | $ | [7 empty] | 1350000 |  |  |  | 600000
7 | Testing and Operations/Monitoring | [16 empty] | 30000 | bar: 2026 Q1 to 2026 Q3; 2029 Q2 to 2029 Q3
|  | $ | [11 empty] | 30000
8 | Pedestrian Infrustructure Study | [16 empty] | 50000 | bar: 2026 Q1 to 2026 Q3; 2028 Q3 to 2028 Q4
|  | $ |  |  |  | $ |  |  |  | 50000 |  |  |  | $
9 | Indirect costs are allowed up to the Tribe’s federally negotiated indirect cost rate. If the Tribe does not have a negotiated rate, indirect costs may be charged up to a maximum of 15% | [16 empty] | 345000
|  | 28750 |  |  |  | 115000 |  |  |  | 115000 |  |  |  | 86250
10 | Administrative: Reporting, Project Management, Invoicing (auto-calculated at 10% of total of project cost, payable to tribe) | [16 empty] | 235500
|  | 4500 |  |  |  | 23500 |  |  |  | 142500 |  |  |  | 65000
GRAND TOTAL FOR PROJECT (not to exceed $3 million) | [17 empty] | 2930500