## 1. Applicant Instructions
Factory Built Housing (FBH) Program
Round 3 Planning Grant Application Workbook
1. Applicant Instructions
Overview
The FBH Program Round 3 Planning Grant Application Workbook includes 5 tabs, outlined below. Planning Grant Applicants must complete this Application Workbook for submission with their FBH Application. The details included in the Application Workbook are intended to support Applicants' narrative responses to the Application and provide reviewers with a full an complete understanding of the Applicant's project proposal. Grey shaded cells have a formula, instructions, or other static content and will be locked for editing.
Tab 1. Applicant Instructions
Tab 2. Workplan
Tab 3. Budget
Tab 4. Example Workplan
Tab 5. Example Budget
How to Complete this Workbook
Tab 1. Applicant Instructions
Review the "Applicant Instructions" and all other Application Workbook tabs before getting started on your Application and Application Workbook. These instructions include details on how to complete each tab in the Application Workbook.
Tab 2. Workplan
1) | This sheet is where you will enter all of your proposed activities for the duration of the 36-month project period. If awarded, the workplan will be used to create your grant agreement. Activities included in the workplan must be detailed with clear ownership, related deliverables, and realistic timelines. Fill out the rows and columns with the requested information. Do not edit any shaded cells, headers, or cells that contain formulas.
2) | All required activities must be addressed in this workplan. The workplan is a set of tasks that align with program objectives, collectively work to achieve the project vision, and is inclusive of the entire grant term.
3) | The workplan should provide a sufficient description of tasks to provide reviewers with an understanding of how specific tasks advance project objectives and goals.
4) | Applicants are not limited to 6 tasks as exemplified in this workplan - include more tasks and subtask as needed.
5) | Timelines should be clear and should not exceed three (3) years. Please note, the Planning Grant Timeline includes a Project Completion Period of 3 years (36 months) from grant agreement execution.
6) | Scoring Criteria: Please see relevant scoring criteria in Section 5 Scoring Criteria of the FBH R3 Final Guidelines to review how your Workplan will be scored.
7) | To view an example on how to complete this worksheet go to Tab #4 "Example FBH Workplan".
Tab 3. Budget
1) | This sheet is where you will enter all budget line items for your proposed project. The budget must align with the activities described in your workplan. Applicants should fill in the white cells only. Do not edit any shaded cells, headers, or cells with formulas included.
2) | Numbers in the "Task #" and the optional "Subtask Number(s)" columns should correspond to the tasks identified in the Workplan.
3) | Cost Descriptions for personnel should clearly identify organizations and positions. For example: “Organization X – Outreach Specialist”, “Organization Y – Senior Project Manager”.
4) | Total Direct Cost will calculate based on the "Cost per Unit" and "Number of Units". Use the "Total FBH Funds Requested" column to indicate the funding you are requesting from FBH grant funds for the line item. The FBH program does require all projects to be fully funded, without funding gaps at time of application.
5) | To add an additional funding source, right click on the column titled "Funding Source 1", and "Insert Table Columns to the Left." This will ensure that the formulas properly extend across all columns.
6) | Use the "Total FBH Funds Requested" and "Other Committed Funds" columns to distribute each budget line item across funding sources.
7) | Total Project Cost will calculate based on the sum of requested direct and indirect costs.
8) | To add more rows, highlight a row desired to be duplicated and select "Insert Rows".
9) | Please note that Federally recognized Tribes may use the indirect cost rate negotiated with the federal government, which may exceed the 10% indirect cost rate cap.
10) | To view an example on how to complete this worksheet go to tab #5 "Example FBH Budget".
Tab 4. Example Workplan
Tab 5. Example Budget
Helpful Links
FBH Program Website
FBH Round 3 Materials
FBH Round 3 Program Guidelines
FBH Submittable Application

## 2. FBH Workplan
FBH Planning Grant Workplan | [6 empty] | Project Schedule: Project Completion Period of 36 months
Instructions
1. Fill out the rows and columns with the requested information. Do not edit any shaded cells, headers, or cells that contain formulas.
2. All required activities must be addressed in this workplan. The workplan is a set of tasks that align with program objectives, collectively work to achieve the project vision, and is inclusive of the entire grant term.
3. The workplan should provide a sufficient description of tasks to provide reviewers with an understanding of how specific tasks advance project objectives and goals.
4. Applicants are not limited to 6 tasks as exemplified in this workplan - include more tasks and subtask as needed.
5. Please note, the Planning Grant Timeline includes a Project Completion Period of 3 years (36 months) from grant agreement execution.
6. Scoring Criteria: Please see relevant scoring criteria in Section 5 Scoring Criteria of the FBH R3 Final Guidelines to review how your Workplan will be scored.
7. To view an example on how to complete this worksheet go to tab #3 "Example FBH Work Plan"
Applicant Information
Lead Applicant:
Proposal Name:
Jurisdiction:
Project Description: (500 character limit)
TASK 1: | [Insert Task Description] | [5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Subtask Number | Subtask Name | Description Include detail of activities or deliverables | Deliverables / Milestones Major outcomes and/or metrics used to demonstrate success | Responsible Parties List primary responsible parties only. | Timeline: Starting Month | Timeline: Ending Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
A
B
C
D
E
TASK 2: | [Insert Task Description] | [5 empty] | 12 12: Project Schedule
Subtask Number | Subtask Name | Description Include detail of activities or deliverables | Deliverables / Milestones Major outcomes and/or metrics used to demonstrate success | Responsible Parties List primary responsible parties only. | Timeline: Starting Month | Timeline: Ending Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
A
B
C
D
E
TASK 3: | [Insert Task Description] | [5 empty] | Project Schedule 12: Project Schedule
Subtask Number | Subtask Name | Description Include detail of activities or deliverables | Deliverables / Milestones Major outcomes and/or metrics used to demonstrate success | Responsible Parties List primary responsible parties only. | Timeline: Starting Month | Timeline: Ending Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
A
B
C
D
E
TASK 4: | [Insert Task Description] | [5 empty] | Project Schedule 12: Project Schedule
Subtask Number | Subtask Name | Description Include detail of activities or deliverables | Deliverables / Milestones Major outcomes and/or metrics used to demonstrate success | Responsible Parties List primary responsible parties only. | Timeline: Starting Month | Timeline: Ending Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
A
B
C
D
E
TASK 5: | [Insert Task Description] | [5 empty] | Project Schedule 12: Project Schedule
Subtask Number | Subtask Name | Description Include detail of activities or deliverables | Deliverables / Milestones Major outcomes and/or metrics used to demonstrate success | Responsible Parties List primary responsible parties only. | Timeline: Starting Month | Timeline: Ending Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
A
B
C
D
E
TASK 6: | [Insert Task Description] | [5 empty] | Project Schedule 12: Project Schedule
Subtask Number | Subtask Name | Description Include detail of activities or deliverables | Deliverables / Milestones Major outcomes and/or metrics used to demonstrate success | Responsible Parties List primary responsible parties only. | Timeline: Starting Month | Timeline: Ending Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
A
B
C
D
E

## 3. FBH Budget
SGC Planning Grant Budget
Instructions
1. Applicants should fill in the white cells only. Do not edit any shaded cells, headers, or cells with formulas included, specifically the entire "Cap/Threshold Summary Table", "Total Project Cost", "Other Committed Funds" and "Check" columns.
2. Numbers in the "Task" column should correspond to the tasks identified in the Workplan.
3. Numbers in the "Subtask Number(s)" column should correspond to the subtasks identified in the Workplan. Applicants are not required to populate this column, though it will help to ensure alignment between the Workplan and Budget.
4. Cost Descriptions for personnel should clearly identify organizations and positions. For example: “Organization X – Outreach Specialist”, “Organization Y – Senior Project Manager”.
5. Total Direct Cost will calculate based on the "Cost per Unit" and "Number of Units". Use the "Total FBH Funds Requested" column to indicate the funding you are requesting from FBH grant funds for the line item. The FBH program does require all projects to be fully funded, without funding gaps at time of application.
6. Maximum Indirect Costs will calculate the maximum amount applicants can request for indirect costs, up to 10% of the total grant award (excluding equipment purchases over $5,000 per unit).
7. Total Requested Indirect Cost will calculate the actual amount applicants have requested for indirect costs.
8. Total Project Cost will calculate based on the sum of requested direct and indirect costs.
9. To add an additional funding source, right click on the column titled "Funding Source 1", and "Insert Table Columns to the Left." This will ensure that the formulas properly extend across all columns.
10.Use the "Total FBH Funds Requested" and "Other Committed Funds" columns to distribute each budget line item across funding sources.
11. To add more rows, highlight a row desired to be duplicated and select "Insert Rows"
12. To view an example on how to complete this worksheet go to tab #5 "Example FBH Budget"
Applicant Information
For the following three rows, information will automatically populate in the associated cell to the right, in column B.
Lead Applicant: | 0
Proposal Name: | 0
Jurisdiction: | 0
This cell is blank, proceed to the table below.
Budget Summary Table | Direct Costs Requested | Indirect Costs Requested | Total FBH Funds Requested
Total Requested | 0 | 0 | 0
Program Threshold and Caps | 90-100% | 0-10% | Total=100%
Calclulated Percentage Check | #DIV/0! | #DIV/0! | #DIV/0!
TASK # | Subtask Number(s) Optional | Cost Category | Cost Description | Cost per unit (Examples: Hourly rates, fees, etc.) | Number of Units (Example: Hours worked, fee cost, number of meetings, etc.) | Unit Type | Total Project Cost | Total FBH Funds Requested | Other Committed Funds | Funding Source 1 | Funding Source 2 | Funding Gap | Fully Funded if FBH grant is awarded?
1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
2 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
5 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
5 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
5 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
5 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
5 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
TOTAL PROJECT DIRECT COSTS | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
MAXIMUM PROJECT INDIRECT COSTS |  | Indirect Cost | Grantees may request reimbursement for indirect costs up to 10% of the total grant award (excluding equipment purchases over $5,000 per unit).The figure in Column I represents the maximum amount of indirect costs available for request. Requests for higher indirect cost rates require prior approval and must include supporting documentation. The 10% maximum of indirect costs applies to all entities, except for Federally Recognized Native American Tribes which may use the indirect cost rate negotiated with the federal government. See Section 3.5: Eligible Costs of the FBH R3 Final Guidelines for more information. |  |  |  |  | 0
TOTAL REQUESTED INDIRECT COSTS |  | Indirect Cost | Enter actual requested indirect costs amount, which can be up to the amount calculated in Maximum Project Indirect Costs in Column I. |  |  |  |  | 0
TOTAL PROJECT COST |  |  | Total Direct Costs + Indirect Costs |  |  |  | 0 | 0 | 0

## 4. Example FBH Workplan
FBH Planning Grant Workplan - EXAMPLE | [6 empty] | Project Schedule: Project Completion Period of 36 months
Instructions
1. Fill out the rows and columns with the requested information. Do not edit any shaded cells, headers, or cells that contain formulas.
2. All required activities must be addressed in this workplan. The workplan is a set of tasks that align with program objectives, collectively work to achieve the project vision, and is inclusive of the entire grant term.
3. The workplan should provide a sufficient description of tasks to provide reviewers with an understanding of how specific tasks advance project objectives and goals.
4. Applicants are not limited to 6 tasks as exemplified in this workplan - include more tasks and subtask as needed.
5. Please note, the Planning Grant Timeline includes a Project Completion Period of 3 years (36 months) from grant agreement execution.
6. Scoring Criteria: Please see relevant scoring criteria in Section 5 Scoring Criteria of the FBH R3 Final Guidelines to review how your Workplan will be scored.
7. *This workplan is a sample of how to use the worksheet.
Applicant Information
Lead Applicant: | Dreaming for Homes
Proposal Name: | Dreaming for More Factory-Built Housing
Jurisdiction: | City of Dreams
Project Description: (500 character limit) | As climate hazards and housing needs continue to compound and disproportionately impact disadvantaged communities, factory-built housing provides an opportunity to combat both issues simultaneously. The project “Dreaming for More Factory-Built Housing” aims to tackle challenges within the existing factory-built housing landscape in the Southern California region, specifically in relation to the City of Dreams and its neighboring jurisdictions. Our organization, Dreaming for Homes, have collaborated with the City of Dreams and two neighboring communities to pilot a streamlined permitting program, to create a pre-approved permitting playbook, and a set of energy-efficient fire-resistant designs for factory-built housing projects to reduce overall planning and development time. Our organization has 20+ years of experience in advocacy for affordable housing for the SoCal region, and we will use SGC funds to complete extensive research to create pre-approved designs and standards that can be replicable and applicable across other jurisdictions. Moreover, we also hope to launch a public education campaign to better educate potential renters and homeowners on the merits of factory-built housing, reducing the historical stigma that factory-built housing is of less superior quality to custom-built homes.
TASK 1: | Develop Permititing Playbook | [5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
Subtask Number | Subtask Name | Description Include detail of activities or deliverables | Deliverables / Milestones Major outcomes and/or metrics used to demonstrate success | Responsible Parties List primary responsible parties only. | Timeline: Starting Month | Timeline: Ending Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
A | Research and stakeholder analysis | Initial assessment: analysis, stakeholder interviews, and associated research to inform the permit playbook. This may include interviews with local jurisdictions, nonprofits, developers, to assess areas of incongruence and possible alignment. Focused on examining the existing processes and how they are or are not working. | 1. Meeting Summaries (date/time/location, number of attendees, summary of outcomes) 2. Summary of findings | Dreaming for Homes | 1 | 8 | bar: 1 1 to 8 8
B | Design charettes/workgroups | Host [total number of] Design Charettes/Workgroups with identified stakeholders to develop permitting playbook | 1. Meeting Summaries (date/time/location, number of attendees, summary of outcomes) 2. Summary of findings | Dreaming for Homes | 8 | 14 | bar: 8 8 to 14 14
C | Finalize playbook | Finalize playbook with stakeholder feedback and research | 1. Final playbook | Dreaming for Homes, Contractor | 14 | 16 | bar: 14 14 to 16 16
TASK 2: | CSS Development: During the first year of the project, the Working Group will engage in facilitated discussions and sessions to work towards establishing CSSs in each focus area that includes residents, partner organizations, and key stakeholders.
Subtask Number | Subtask Name | Description Include detail of activities or deliverables | Deliverables / Milestones Major outcomes and/or metrics used to demonstrate success | Responsible Parties List primary responsible parties only. | Timeline: Starting Month | Timeline: Ending Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
A | Engage partners and discuss roles and interests | Project team will engage partners one-on-one or through small group meetings to share project scope and goals and discuss collaboration and opportunities for involvement. | 1. Meeting Summaries (date/time/location, number of attendees, summary of outcomes) | Dreaming for Homes | 1 | 12 | bar: 1 to 12
B | Establish a standing Working Group meeting and initiative development of a Collaborative Stakeholder Structure (CSS) | The project team will work with partners to coordinate a standing meeting that will include partners across the multiple jurisdictions. The project team will prepare meeting agendas, bring in outside speakers if appropriate, facilitate meetings, take notes, and advance the group forward. | 1. Meeting Summaries (date/time/location, number of attendees, summary of outcomes) | Dreaming for Homes | 1 | 20 | bar: 1 to 20
C | Draft MOU/ Partnership Agreement to formalize CSS | The Project team will support the Working Group in Drafting a Partnership Agreement/MOU to formalize roles for each CSS. This will be a collaborative process that is based on joint priorities, values, and understanding of the group. | 1. Report on findings | Dreaming for Homes, City of Dreams, County of Dreams | 1 | 20 | bar: 1 to 20
TASK 3: | Project Management & Grant Administration: This task represents the ongoing staffing towards ongoing project management and grant administration throughout the lifetime of the grant period, including regular progress reporting and evaluation, among other requirements for successful grant administration.
Subtask Number | Subtask Name | Description Include detail of activities or deliverables | Deliverables / Milestones Major outcomes and/or metrics used to demonstrate success | Responsible Parties List primary responsible parties only. | Timeline: Starting Month | Timeline: Ending Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
A | Grant Administration, reporting & invoicing | Ongoing grant administrative tasks throughout the project, including reporting and invoicing. Produce narrative and financial reporting per grant agreement to highlight project progress on milestones, deliverables, and expenditures within budget. Preparation of quarterly invoices for reimbursement. | Quarterly progress reports. Quarterly invoices. | Dreaming for Homes | 1 | 35 | bar: 1 to 35

## 5. Example FBH Budget
FBH Planning Grant Budget - EXAMPLE
Instructions
1. Applicants should fill in the white cells only. Do not edit any shaded cells, headers, or cells with formulas included, specifically the entire "Cap/Threshold Summary Table", "Total Project Cost", "Other Committed Funds" and "Check" columns.
2. Numbers in the "Task" column should correspond to the tasks identified in the Workplan.
3. Numbers in the "Subtask Number(s)" column should correspond to the subtasks identified in the Workplan. Applicants are not required to populate this column, though it will help to ensure alignment between the Workplan and Budget.
4. Cost Descriptions for personnel should clearly identify organizations and positions. For example: “Organization X – Outreach Specialist”, “Organization Y – Senior Project Manager”.
5. Total Direct Cost will calculate based on the "Cost per Unit" and "Number of Units". Use the "Total FBH Funds Requested" column to indicate the funding you are requesting from FBH grant funds for the line item. The FBH program does require all projects to be fully funded, without funding gaps at time of application.
6. Maximum Indirect Costs will calculate the maximum amount applicants can request for indirect costs, up to 10% of the total grant award (excluding equipment purchases over $5,000 per unit).
7. Total Requested Indirect Cost will calculate the actual amount applicants have requested for indirect costs.
8. Total Project Cost will calculate based on the sum of requested direct and indirect costs.
9. To add an additional funding source, right click on the column titled "Funding Source 1", and "Insert Table Columns to the Left." This will ensure that the formulas properly extend across all columns.
10.Use the "Total FBH Funds Requested" and "Other Committed Funds" columns to distribute each budget line item across funding sources.
11. To add more rows, highlight a row desired to be duplicated and select "Insert Rows"
12. *This budget is a sample of how to use the worksheet.
Applicant Information
For the following three rows, information will automatically populate in the associated cell to the right, in column B.
Lead Applicant: | Dreaming for Homes
Proposal Name: | Dreaming for More Factory-Built Housing
Jurisdiction: | City of Dreams
This cell is blank, proceed to the table below.
Budget Summary Table | Direct Costs Requested | Indirect Costs Requested | Total FBH Funds Requested
Total Requested | 112750 | 10000 | 122750
Program Threshold and Caps | 90-100% | 0-10% | Total=100%
Calclulated Percentage Check | 91.85% | 8.147% | 100%
TASK # | Subtask Number(s) Optional | Cost Category | Cost Description | Cost per unit (Examples: Hourly rates, fees, etc.) | Number of Units (Example: Hours worked, fee cost, number of meetings, etc.) | Unit Type | Total Project Cost | Total FBH Funds Requested | Other Committed Funds | Funding Source 1 | Funding Source 2 | Funding Gap | Fully Funded if FBH grant is awarded?
1 | B | Supplies | Materials & supplies for meetings | 300 | 5 | Meeting | 1500 | 1500 | 0 | 0 | 0 | 0 | TRUE
1 | B | Subcontractors | Facilitator for meetings | 150 | 10 | Hours | 1500 | 1500 | 0 | 0 | 0 | 0 | TRUE
1 | A, B, C | Grantee Personnel | Dreaming of Homes - Project Manager I | 85 | 150 | Hours | 12750 | 12750 | 0 | 0 | 0 | 0 | TRUE
1 | A, B, C | Grantee Personnel | Dreaming of Homes - Project Manager II | 120 | 150 | Hours | 18000 | 18000 | 0 | 0 | 0 | 0 | TRUE
2 | B | Supplies | Materials & supplies for workgroups | 300 | 12 | Fee | 3600 | 3600 | 0 | 0 | 0 | 0 | TRUE
2 | B | Travel | Travel costs for workgroups | 400 | 12 | Fee | 4800 | 4800 | 0 | 0 | 0 | 0 | TRUE
2 | A, B, C | Grantee Personnel | Dreaming of Homes - Project Manager I | 85 | 120 | Hours | 10200 | 10200 | 0 | 0 | 0 | 0 | TRUE
2 | A, B, C | Grantee Personnel | Dreaming of Homes - Project Manager II | 120 | 120 | Hours | 14400 | 14400 | 0 | 0 | 0 | 0 | TRUE
3 | A, B, C | Grantee Personnel | University of Hummingbird - CFO | 150 | 240 | Hours | 36000 | 36000 | 0 | 0 | 0 | 0 | TRUE
3 |  | Large Equipment (>$5k) | Front end loader | 10000 | 1 |  | 10000 | 10000 | 0 | 0 | 0 | 0 | TRUE
3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
3 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
4 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
5 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
5 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
5 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
5 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
5 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | TRUE
TOTAL PROJECT DIRECT COSTS | [6 empty] | 112750 | 112750 | 0 | 0 | 0 | 0 | TRUE
MAXIMUM PROJECT INDIRECT COSTS |  | Indirect Cost | Grantees may request reimbursement for indirect costs up to 10% of the total grant award (excluding equipment purchases over $5,000 per unit). The figure in Column I represents the maximum amount of indirect costs available for request. Requests for higher indirect cost rates require prior approval and must include supporting documentation. The 10% maximum of indirect costs applies to all entities, except for Federally Recognized Native American Tribes which may use the indirect cost rate negotiated with the federal government. See Section 3.5: Eligible Costs of the FBH R3 Final Guidelines for more information. |  |  |  |  | 11416.6667
TOTAL REQUESTED INDIRECT COSTS |  | Indirect Cost | Enter actual requested indirect costs amount, which can be up to the amount calculated in Maximum Project Indirect Costs in Column I. |  |  |  |  | 10000
TOTAL PROJECT COST |  |  | Total Direct Costs + Indirect Costs |  |  |  | 122750 | 122750 | 0

## Data Validation Tab (hidden)
FBH Reference: Data Validation Tables
Data Validation Tables - Do not edit
Cost Categories
Grantee Personnel
Supplies
Co-applicants/Partners Personnel
Subcontractors
Travel
Large Equipment (>$5k)
Other Direct Cost
Unit Type
Project
Hours
Days
Weeks
Months
Year
FTE
Fee
Plan
Report
Meeting
Mile
Item